TKE Tac32 Holeless Hydro Task List

|  | Pre-work Safety Checklist |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Fall Protection Plan (job packet) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Hang fire signal sheet |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | JHA (Daily) |  |  |  |  |  |  |  |  |  |  |  |
|  | Finished floor heights |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Cab pads receipt |  |  |  |  |  |  |  |  |  |  |  |
|  | Survey Hoistway |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Pump Unit, use isolation pads |  |  |  |  |  |  |  |  |  |  |  |
|  | Safety lifeline & rigging |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Pit Template |  |  |  |  |  |  |  |  |  |  |  |
|  | Rail Brackets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | D.B.G. stick |  |  |  |  |  |  |  |  |  |  |  |
|  | Piston brackets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Rails, splice tubes and bolts – flat file ends |  |  |  |  |  |  |  |  |  |  |  |
|  | Add oil |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Cylinders |  |  |  |  |  |  |  |  |  |  |  |
|  | Run button |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Assemble oil line |  |  |  |  |  |  |  |  |  |  |  |
|  | Bleeders, drain tube hardware, tape to jacks. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Bleed system |  |  |  |  |  |  |  |  |  |  |  |
|  | Buffer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Car frame (bottom) |  |  |  |  |  |  |  |  |  |  |  |
|  | Sway braces |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Guide shoes, platen plates, hardware |  |  |  |  |  |  |  |  |  |  |  |
|  | Platform |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Finish rails and brackets |  |  |  |  |  |  |  |  |  |  |  |
|  | File rail joints |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Set D.B.G. |  |  |  |  |  |  |  |  |  |  |  |
|  | X-head EQ Brackets on AMEE’s |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Finish carframe, Crosshead stickers |  |  |  |  |  |  |  |  |  |  |  |
|  | EQ brackets on guides |  |  |  |  |  |  | Top |  |  |  |  |  | Bottom |  |  |  |  |  |  | Oil in guides, (SAE 30) |  |  |  |  |  |  |  |  |  |  |  |
|  | Adjust platform 6 ¼” s.s. 7 ¾” t.s. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Top selector bracket - pin. |  |  |  |  |  |  |  |  |  |  |  |
|  | Entrance angles |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Lasers, anchors, lags, Get jambs ready. |  |  |  |  |  |  |  |  |  |  |  |
|  | Pit ladder – make sure it doesn’t hit car sill. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Fronts, then prepare doors, peel plastic off edges |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Jambs |  |  |  |  |  |  |  |  |  |  |  |
|  | Install Braille (drill or sticky) 60” center |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Doors and related hardware/equipment |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 ½” Emt from controller to hoistway |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Raceway and 3/4 “ Emt |  |  |  |  |  |  |  |  |  |  |  |
|  | Traveling cable hanger |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Strip traveling cable |  |  |  |  |  |  |  |  |  |  |  |
|  | Hoistway piping and flexing. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Hall boxes – 42” center of button(s) |  |  |  |  |  |  |  |  |  |  |  |
|  | Dynamic & Static sensors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Wire Hoistway |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Cover wires in hall boxes with cardboard |  |  |  |  |  |  |  |  |  |  |  |
|  | Selector |  | Mark floors |  |  |  |  |  |  |  |  |  | Magnets |  |  |  |  |  |  |  | Cab Prep: transom, strike jamb, strip handrails. |  |  |  |  |  |  |  |  |  |  |  |
|  | Fascia |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Put stickers on job & Brady markers |  |  |  |  |  |  |  |  |  |  |  |
|  | Check platform for level |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CAB UP |  |  |  |  |  | Call to schedule truck pickup (1-2 days left) |  |  |  |  |  |  |  |  |  |  |
|  | Install cab steadiers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Car door (s) |  |  | Hardware |  |  |  |  |  |  |  |  |
|  | Install Light tubes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Mount water sensor 1’ off pit floor |  |  |  |  |  |  |  |  |  |  |  |
|  | Cartop wiring |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Pit cans. Label lids, cut excess drain tube. |  |  |  |  |  |  |  |  |  |  |  |
|  | Cartop light bulbs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Toe guard(s) |  |  |  |  |  |  |  |  |  |  |  |
|  | Handrail required on cartop if over 12” |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Hang traveler to car. |  |  |  |  |  |  |  |  |  |  |  |
|  | Install ceiling |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Wire C.O.P. |  |  |  |  |  |  |  |  |  |  |  |
|  | Wire Controller |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Install Repps system |  |  |  |  |  |  |  |  |  |  |  |
|  | Clean up & Paint anything needing it |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Store unused parts in car or controller |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Fill out Contractor’s Responsibility list |  |  |  |  |  |  |  |  |  |  |  |

Pendant Light – Verify not wired to load side of GFCI

Emergency Power requires additional signal, check print.

Notes:__________________________________________________________________________________

_______________________________________________________________________________________